## Plan & Resource summary
Plan | Week1 | Week2 | Week3 | Week4 | Week6 | Week7
Requirements | bar: Week1
Env Prep | bar: Week1
Design | bar: Week1
Development | bar: Week2 to Week4
Unit Testing | bar: Week6
Deployment | bar: Week7
Integration Test | bar: Week7
Resource load | Week1 | Week2 | Week3 | Week4 | Week6 | Week7
Lead | bar: Week1 to Week7
Devloper1 | bar: Week1 to Week7
Devloper2 | bar: Week2 to Week6
Developer3 | bar: Week2 to Week6

## Efforts Estimation
Efforts (PDs)
Requirments | Detailing and clarifications | 3
Design & Documentation | Design and Documentation (Service Spec,Data Modeling,Solution design, Functional Spec etc) | 5
Dev Environment preparation | SCM | 1
| Project structure | 1
Customer | Dashboard (List of claims, graphs etc) | 6
| FNOL Initiation/processing / details submission | 5
| Repair shop selection | 4
| OOP or Claim Selection | 3
| Schedule Appointment and Drop Vehicle | 4
Repair Shop | Dashboard | 3
| Receive/Validate FNOL | 2
| Access car damage details | 2
| Replace Vs Repair Procesing and Estimation | 2
| Query resolution | 3
| Vehicle Repairing | 2
| Notification to Insurer and Policy Holder once car gets repaired | 2
| Invoicing | 2
Insurer | Dashboard | 3
| Validate FNOL/Policy | 2
| View/Review Estimates | 2
| Notification to Policy Holder | 2
| Claim Creation & Claim Processing | 5
| Queries with Repair shop | 3
User Management | User Authentication | 3
| Authorization | 2
Testing | Functional testing and Bug fixing | 4
| Integration testing and Bug fixing | 2
Environment/Cloud Setup | Provisioning compute and storage | 2
Network Setup | Network Generation | 5
Node configuration
Ecosystem Integration
Policy and Permissions | Asset,Policy and Permissions deployment on DLT network | 5
Packaging and Deployment | Application bundling | 5
Docker container/ VM management
Deployment script
| UAT | 2
| Total | 97