## Slide 1: Intercompany Sundry Accounting & FCCR Cost Centre Creation Blockchain
24 July 2018

## Slide 2: Objectives of Session
Map out key variants to FCCR Process and Sundry process
Agree series of workshops to provide technical team with detail
Agree ways of working

## Slide 3: Key design decisions/ principles
As in our POC we need to make clear design principles for this pilot
1) The pilot and eventually global solution will be developed to minimise reliance and impact on UL systems
2) It is a disruptive innovation project – the approach is to start with exploring difficult questions and if the result is unsatisfactory or issues cannot be resolved, we will stop.
3) Minimise impact on UL user where possible, ensure change management is agreed with UL user
4) Scope, Global Sundry and FCCR IC solution
5) Hosting, Capgemini hosted solution
6) Out of Scope, Real time SAP integration

## Slide 4: FCCR Cost Centre Creation – Process Steps
CG FCCR Team
FTE 4.0
CG MDM Team
FTE 1.5
Unilever
Volume (Monthly)
Individual – 375-450
(via Share-point)
Mass Creation – 300
(via Mails)
Raise Individual Cost Centre Creation Request
Raise Mass Cost Centre Creation Request
Query Resolution
Receive the request raised through Share-point.
Validation Check (rule based)
Fill in the
Standard Template
Input the data manually in BMC tool for U2K2, Fusion & Cordillera platform
Fill in the details in MDG tool for Sirius platform which interface with SAP
MDM Team will receive the BMC ticket
Validate the request
Process the validated details by manually keying in SAP
? Query
! Dependency on ICC Creation
Normal Request
Request having query
Share Point
Request Validation
Additional
Details Required
1
3
2
4
5
6
8
7
9
10
MDM
Request
MDM Turnaround Time
For Cost Centre Creation
?!
1
3
2
4
5
6
8
7
SLA
Individual cost code– 2 days initial response
Within 8 days receipt of request cost centre should be created. Ideally 3-4 days
Mass Creation – 10 days
No agreed SLA
Multiple Touchpoints
Turnaround
Time (days)
Approval and re-raise cycles, issues and query resolutions can delay the cost centre creation process
Alternative MDM Teams
UL MDM Team Cordillera: will transition to Capgemini
UL MDM Team CODA (non SAP) will always be UL no MDG and UL OUT OF SCOPE
*Robo needs to interact with MDG layer, interface with SAP; data direct to SAP. MDG has built in validation.
Decision: Sanjoy approved; in future end state flow for this process with have MDG rolled out to all platform (bar CODA) therefore in Blockchain workflow we will NOT include CG MDM team in the flow.
We will include UL MDM team, possibly out of scope pending MDG roll out
Assumption:
UL will complete transition of all MDM services to CG
UL will implement MDG in all SAP platforms
Validations use Master from SAP (x4), download from MDM team.
Monthly process to download. Cross check manually refer to sheet.
Query resolution:
Types of queries,
Receive request to close cost centre, go back and check balances in cost centre, that case respond to requestor still balance in SAP what action next? If tracking mechanism. Validation into system submit then errors respond to user
Initial request, needs to state when the cost centre will be active from
UL user can create a cost centre for any region and any country, no segregation needed
Mass upload, can Blockchain feature, upload excel to auto populate fields? For multiple cost centres.
Reconciliation request, possible to make sure cost centre in SAP match what is available
MDM for cost centre, how will it get into Blockchain to update master data?
CJ Q: Robo to pull data, weekly? Run on all three platform
Tracking required, and reporting of live status** Feature required
Report needs to show how many request “happy path” and how many re raised due to a,b,c
User and access mmgt strategy for all UL and CG users

## Slide 5: As-Is process highlights pain points

## Slide 6: What does the tech team need to proceed? FCCR
Any further information required from the tech team to proceed?
Detailed captured in request (single and multi upload)
What kind of validation is completed?
Master data from sap
Format in MDG file?
Bulk update format excel provided
Example of email for bulk upload
Variations in validation based on country or region?
Sanjoy/Jackie to help share videos of the end to end process with team

## Slide 7: What does the tech team need to proceed? Sundry
Any further information required from the tech team to proceed?
Jon to create matrix of various options (AP/AR per platform in happy path)
Version 2 will map country to country (Devendra, what format best for you?)
Screen to create request in Blockchain changes in screen need to be identified per country DETAILs required (Wasim/ Jon)
Devendra to review flow and include exceptions
RPA clearly how integrate with Blockchain and Sharepoint etc What are trigger point? Functionality in Blockchain and RPA agreement on what scope per RPA **Session with CJ tech discussion dev Sachin and Devendra Dan to book
Identify what is NOT automated (any manual approval/checks)
Call out change in process, change mmgt process identified and documented
% of automation Wasim…. Jackie/Jon/Dan to collate list for Wasim of those steps not automated as part of the process. Various types of exceptions, dev perspective code for specific countries configuration
Master data strategy, need to CJ document how robos help keep MDM for Sundry and FCCR whole solution approach
Reporting for Sundry features, Wasim to share the current reports to tech team

## Slide 8: Next steps: Week 1 and Week 2
With such a short delivery timeline we need to ensure each week has a clear deliverable
Owner | Deliverable | Due Date | Status/ Update
Devendra and Sachin | Detailed solution design | 31/07/2018 | Open
Devendra and Sachin | Design Infrastructure diagram | 31/07/2018 | Open
Daniel and Jon | User Story workshop | 30/07/2018 | Open
Devendra and Sachin | Outline Infrastructure requirements | 31/07/2018 | Open
Scrum Team | Sprint Planning | 31/07/2018 | Open
Owner | Deliverable | Due Date | Status/ Update
Daniel | Kick Off and Ways of working session | 27/07/2018 | Open
Daniel | Confluence and JIRA set up, daily scrum calls, sprint review sessions | 27/07/2018 | Open
Wasim and Sanjoy | Share all process knowledge with tech team to enable detailed design | 27/07/2018 | Open
Week 1: w/c 23rd July
Week 2: w/c 30th July

## Slide 9: Ways of working during an Agile project
Once business and tech teams are mobilised we need to decide ways of working; noting end of the month teams will be heavily occupied
Scrum Meeting | Purpose | Frequency | Attendee Required
Daily Huddles | Daily catch up with the Scrum Team to share what they did yesterday, what they plan on doing today and any blockers Pune Development team will also have daily huddles AM India time and follow up with UK team later in the day | Daily 10:30 UTC | Scrum Team
Sprint Kick Off | Weekly Sprints have been decided; at the beginning of each Sprint, a brief planning session takes place in which the backlog items for the sprint are selected. | Monday's | Dev + PO
Show n Tell | By the end of a sprint, the team demonstrates the increment to the Product Owner and Stakeholders. Feedback is gathered as to make the necessary improvements to the product and the process. | Friday's | Dev Lead+ PO
Retrospective | A brief "lessons learned" meeting takes place, at which all team members review the sprint with Scrum Master. The purpose of this meeting is to identify what worked well and what didn't work well and identify what needs to be done to address the problems. This results into team-resolvable and organizational impediments and next steps to solve them. | Friday's | Scrum Team
Backlog Refinement | Product backlog refinement is the process through which product backlog items are reviewed by the Scrum team and revised, providing more detail and ensuring that there is greater clarity in the requirements for that item. | Friday's | Dev+ 1 PO
Scrum of Scrums | Scrum master from off shore and UK to meet to prepare Sprint review and backlog refinement | Thursday's | TBC + Daniel

## Slide 10: Detailed Plan for the POC
Milestone
Supporting Activity
Workshop/ Meeting
Key
Technology
Business Processing
Preparation Phase |  |  |  | Development and Testing Phase |  |  |  |  |  |  |  | Implement
Week -1 | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
w/c 16th July | w/c 23rd July | w/c 30th July | w/c 6th Aug | w/c 13th Aug | w/c 20th Aug | w/c 27th Aug | w/c 3rd Sept | w/c 10th Sept | w/c 17th Sept | w/c 24th Sept | w/c 15th Jan | w/c 1st Oct
Change Management
Governance
Tech Demo
Define Scope
Kick Off
Session
Prep Calls to define high level plan
Recommendation on POC
Develop Hypothesis on POC Outcomes
Confirm as-is architecture
1st Business User story workshop
Daily Stand up call with scrum team @ 10:30 CET
Identify Partner in UL
Agree WoW during POC
Establish KPIs
Start to define To- be Architecture
Identify impact on business and end user
Define details business rules
2st Business User story workshop
Test MVP
Test UAT
Define Proposed App Arch
Compile recommendations
Report back business outcomes & impact
Share insights and learnings with Unilever
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint 3 Complete
Sprint 4 Complete
Kick Off
With Client
Development Sprint 1
Daniel Cannon
IC and FCCR Team
Devendra and Team
Catherine Jenkins
Design Sprint 1 Complete
Sprint
Showcase
/Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint 5 Complete
Sprint 6 Complete
Sprint 7 Complete
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase
/Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase
/Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint
Showcase/
Retro
Sprint 3 Complete
Sprint 4 Complete
Sprint 5 Complete
Sprint 6 Complete
Sprint 7 Complete
Design Sprint 1 Complete
Development Sprint 2
Sprint 2 Complete
Sprint 2 Complete
Development Sprint 3
Development Sprint 4
Development Sprint 5
Development Sprint 6
Design Sprint 1
Design Sprint 2

## Slide 11: High level 12-week delivery plan
Business
Technical
Change Mmgt
End to End detailed design confirmed with UL and CG users
Establish features required, reporting?
Access groups defined, access and who from UL and CG
Agree wireframe look and feel of tool
Confirm technical design decisions
hosting, SAP integration
Assess how much of the original POC can be reused
Establish an access management strategy
Call out Master data strategy/ work around with SAP
Build communication strategy
Build training material on new tool/process
Create plan on how to deliver training to user groups
Attend Agile sprints for weekly input into design
Support development of training materials and change management efforts on UL and CG
Develop based on established user stories/ features
Build on exiting components from the IC PoC
Delivery training sessions with end users of FCCR and IC processes
Send communications plan of incoming change
Support market in adoption of the new tool
Monitor performance
Test reporting with live data
Monitor user experience
Send follow up communication
Hold support training sessions
Answer FAQs via portal
Mobilisation and Design (3-4 wks)
Development (4-6 wks)
Implementation (1-2 wks)
Over the next 12-weeks we will be building out this plan in more detail through Agile WoW

## Slide 12: What does the business team need to proceed?
Verdict: Technically feasible, detailed design required
Sign off: Wasim and Devendra (in principle)
1)Invoice processing for Cross platform and Within platform. All the current process flow models need to be covered (Attached is the first draft of the Model by ERP Platform – End to End steps by Country)
Initial review completed by tech team Devendra and Sachin
No major concerns in incorporating variations into Blockchain at this stage
Deep dive into country variations meeting Tuesday 24/07
Service Recipient (AP country) logs into Blockchain to request a service from Service provider (AR country)
Smart contract executed and tool created Order # and send SAP signal to create an invoice
Request routed to Counterparty approver account within Blockchain for approval (AP Country)
In case of query Blockchain would notify AP country and queries/response logged here
Service request approved AP posting in SAP by Robo
Robo uploads data into SAP FI or SD and provides BC with invoice # to be stored
Robo saves invoice’s created after AR posting in ShareDrive and attach to AP/AR posting
Service request closed and reflected on dashboard

## Slide 13: What does the business team need to proceed?
FI Module
Verdict: Technically feasible, detailed design required
Sign off: Wasim, CJ, Devendra
2) The processing in SAP is either by FI module or SD module. SD module has additional steps before AR processing – manual SO creation.
  Performed through RPA, @CJ has verified technical feasibility
  This process needs to be seamless incorporated into the rest of the Blockchain process
  Deep dive required country wise and also the process called out in this slide needs to be stitched with the process defined in the Slide No.1
Blockchain application to send AP and AR data via Flat file transfer
Robot Picks up data from folder
Robot processing AR and AP data into SAP platform
SAP U2K2
SAP Fusion
CODA
Robot input into SAP format required
SD Module
SAP Sirius
SAP Cordillera
CODA
Service request approved by both AP and AR
Technical Inputs
Firewall issue possible between folder and robot need to include UL IT here to open certain ports
ETL interface, talk to application folder and load into UL environment
Extract, transform and load data SAP
Blockchain app will send batches to the robot, every hour purposed and approved by Wasim
SAP format
Only sending info, robo is not doing any validation
Into two different platforms in two different geo’s possibly
Robo role posting into SAP, technically feasible
FI, one step and SD module, two steps execute sales order and create invoice
Extract of Proposed Process:

## Slide 14: What does the business team need to proceed?
Verdict: Technically feasible, detailed design required
Sign off: Wasim, CJ, Devendra
3) Invoice copy attached in SAP after respective posting / saved into Blockchain layer / placed in Shared drive as per the specified requirement.
After AR posting invoice generated by SAP and this invoice needs to be saved to SharePoint (because of legal requirements for countries, list of countries for at least 10 years, iron mounting contract retain as hard copy) and invoice attached on AP posting reference in SAP.
Effort to complete this task 2-3mins per invoice
Some countries invoice is generated manually, some are automate, create excel based invoices
This process needs to be seamless incorporated into the rest of the Blockchain process
CJ confident this can be performed by robo, detailed design required at later stage
Blockchain application to send AP and AR data via Flat file transfer
Service request approved by both AP and AR
Robot has posted AR posting (#2)
Invoice is automatically created in SAP
Invoice is manually created using excel created
Invoice needs to be saved on Shared drive
Invoice needs to be attached to corresponding AR posting in SAP
Invoice needs to emailed to IronMountain
Invoice needs to be attached to corresponding AP posting in SAP
Technical Considerations
Invoice posting done by robo
Sirius and Corderillera automatically populated SAP to create invoice (SD module)
U2K2 and Fusion needs robo to create invoice (FI Module)
Blockchain needs to provide country specific data dump and then input into country template, save on shared drive and then attach into SAP
Any changes to the country specific template will impact robo performance, and require a CR to amend
Extract of Proposed Process:

## Slide 15: What does the business team need to proceed?
Verdict: Feasible as part of change mmgt plan, ask Country Tax teams to check Blockchain
Sign off: Wasim and Devendra
4) Manual Touch points / Exception scenarios are incorporated within Blockchain layer. This will help achieve FPY of 95%+ for Sundry Invoicing:
  4.1 WHT confirmation process incorporated into the Blockchain portal including follow up mail triggers for approval to Country Tax team for AP posting
  Notification within Blockchain on the dashboard, download invoice from blockchain to check don’t need to attach in emails. Log into blockchain and all details within RIGHT after AR posting, and then direct for AP posting. Confirm comments section, flexibility for the approver.
  Include in change mmgt to check blockchain daily/weekly get tax approver groups on board with this (user group so log in and password per country) Aligned with Wasim and Uday
Invoice is created on Blockchain
Country Tax approver notified via Blockchain dashboard
Country Tax user views invoice in Blockchain
Country Tax user approves/rejects request in Blockchain
Request is triggered for AP processing
Service request is sent back to AR country via dashboard
Proposed Process:

## Slide 16: What does the business team need to proceed?
Verdict: Technically feasible, detailed design required
Sign off: Wasim, CJ, Devendra
4)
  4.2 After AR posting, Invoice copy is generated by Country on their Letter head and sent back to CG AR team, for further processing by AP team (the same needs to be a notification or download trigger to be sent to a specified contact from Country team)
  How many countries 20 countries… figures on the number of request? 150 request monthly total. Countries legal requirement needs to be printed in their country and manual signature possible, convert to PDF and email back to CG team, attached PDF into SAP in AR and AP posting.
  Blockchain this data pick up and send to printer, this part is feasible
  Picking up PDF attachments, shared drive link unique reference number PDF attachment link within blockchain firewalls
  Robo picks up form share drive, and attached to AP/AR SAP respectively
Country team receives email with invoice info
*Possible RISK this will not be easily checked if the right document was uploaded correct
Technical Considerations
Size of attachments could be an issues here for robo to process and attach into SAP AR and AP
Proposed Process:
Invoice is updated within SAP (#2)
Robot attached invoices in SAP
Blockchain sends trigger to Country team invoice is ready to be printed/signed
Trigger to request WHT
Country team manually prints, signs invoice
Country clicks link within BC and linked to Sharepoint
Country saves PDF on Sharepoint*
Country ticks box in blockchain action complete
Country logs onto Blockchain to ‘save’ the PDF invoice
Trigger to AP processing

## Slide 17: What does the business team need to proceed?
Verdict: Technically feasible as part of smart contract, MDM strategy required sign off
Sign off: Wasim and Devendra
4)
  4.3 Operational issues due to the template submission being incorrect – Cost center issue, GL code issue, Tax code issue, GRN not created for PO based invoices (All of these need to be validated at Request submission level and not move to next step, so that FPY is far improved).
  Master data from each platform needs to be pulled by Blockchain from the shared drive
  Blockchain will need to keep Master data separated per platform via back end and use this data for real time validation and to execute smart contracts
  Tech team and business team need to agree how often Blockchain will pull data from the folder
  Possible robotic add on the pull Master data from platforms more frequently, current happens monthly
Blockchain pull weekly MDM from Folders
Blockchain uses MDM in smart contracts
Shared drive store of 5 platforms MDM
SAP Sirius MDM
SAP Coridllera MDM
SAP Fusion MDM
SAP U2K2 MDM
CODA MDM
Manual upload to folder weekly

## Slide 18: What does the business team need to proceed?
Verdict: Technically feasible
Sign off: Wasim and Devendra
5) Model to cover Rule Based Invoicing i.e. Repeated Monthly invoicing for a specified period based on one time approval.
Discussed with Devendra and Sachin, within Blockchain we can run monthly repeated invoice.
Month on month we need to repeat the transaction but the amount is different, which is manually inputted. This can be the trigger to run the monthly invoices based on pre-defined criteria
We will create a standard template so when a requestor clicks on a “ Run XYZ monthly invoicing” they don’t need to approve again but just change the amount.
Feature Design decision: create a template so it can copy from previous approved invoice, go forward without approval, and allow for changing the amount.
6) Basis the above, it should be a Zero touch invoice processing (with the proposed RPA solution) . 10% of manual tracking is expected during stabilization phase and 5% during BAU mode after solution implemented.
Purposed RPA processing of invoices to SAP is outlined in question 2).
This KPI will serve as a metric throughout the Pilot
7) Dashboard reporting same as BMC – Status of requests (by request and by stage of processing) , Reports generation for Month end Accruals for the On hold invoices and KPI’s.
Was a key feature in POC but didn’t have time to develop. To build the reports, Devendra’s team needs the report we want to generate. Normally we get data from Blockchain to data store and do the reporting from there.
Action: Wasim to send reports and Devendra to evaluate the solution

## Slide 19: FCCR and Sundry invoicing high level process flows
If AP country raises query, resolved manually via email and updated in SAP
AP country approves request if required via email & BMC
Request initiated in BMC by AR country or CG
AP country to request service via email from AR country
AR agent manually processes request in BMC and SAP
AR agent and AP country exchange emails re cost, cost-codes, approvers
AP agent manually processes request in Excel, BMC and SAP
Service Recipient (AP country) logs into Blockchain to request a service from Service provider (AR country)
Smart contract executed and tool created Order # and send SAP signal to create an invoice
Request routed to Counterparty approver account within Blockchain for approval (AP Country)
In case of query Blockchain would notify AP country and queries/response logged here
Service request agreed/ closed by AP and AR countries
UL to raise new cost code request via SharePoint or email
CG FCCR manually pull data, update cost codes, and perform validation checks
Back and forth query resolution between CG FCCR and UL teams
CG FCCR to Complete BMC template with UL approval, re-raise if incorrect
CG MDM team create cost code, CG FCCR check and re-start if incorrect
Sundry Invoicing
Cost-centre creation
No direct update when cost-centre is created
As-is
To-be
Create request in Blockchain, Smart contracts for validation
Feed data into template in Blockchain for UL approval, auto-send to MDG tool and SAP
Cost-code created updated in Blockchain for all parties and master data with new
Sundry Invoicing
Cost-centre creation
We will be developing robotics to aid in the SAP integration
Number of platforms reduced from 5 to 2
Number of steps in both processes reduced significantly

## Slide 20: Org Chart for the Pilot

## Slide 21: Exec Summary of the Pilot
This exec summary should be inclusive of the FCCR and IC process
Inefficiency in processing (Turnaround time and Quality)
Accruals at month end
Unreconciled intercompany balances
Delays in settlement
Manual interventions required to raise service requests between countries across different SAP platforms, different data sources and tools use (BMC Remedy, Excel, Emails)
Resulting in a business impact…
Reduced manual effort of processing
Reduced lead time of processing
Simplify system complexity and touchpoints
Improve user journey and experience
Tested the following hypothesis
Problem Statement