## Plan & Resource summary
Plan | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7
Requirements | bar: Week1
Env Prep | bar: Week1
Design | bar: Week1 to Week2
Development | bar: Week2 to Week5
Unit Testing | bar: Week6
Deployment | bar: Week7
Integration Test | bar: Week7
Resource load | Week1 | Week2 | Week3 | Week4 | Week5 | Week6 | Week7
Lead | bar: Week1 to Week7
Devloper1 | bar: Week1 to Week7
Devloper2 | bar: Week2 to Week7
Devloper3 | bar: Week2 to Week6

## Efforts Estimation
Efforts (PDs)
Requirments | detailing and clarifications | 3
Design & Documentation | Design and Documentation (Service Spec,Data Modeling,Solution design, Functional Spec etc) | 5
Dev Environment preparation | SCM | 1
| Project structure | 1
Interface simulators | Services for ref data , external events and oracles | 5
External weather observer | componenet to observer external sources | 5
GPS / location processor | Location and GPS mapping processing | 5
Customer | Claim Creation | 5
| Claim validation | 3
| Calamity validations | 3
| claim processing using smart contracts | 5
Repair Shop | Claim validation | 2
| Policy details provision to smart contracts | 3
| Calamity validations | 2
Insurer | Claims validation | 2
| policy validation | 2
| disaster validation | 2
| claim processing using smart contracts | 5
| payouts | 3
External weather observer | componenet to observer external sources | 5
GPS / location processing | mapping the GPS details to the policy holders | 3
Integration | Integration with weather observating component and event triggering | 5
| Integration with with each of the guidewire systems for sub systems | 5
Interface simulators | Services for ref data and oracles | 3
Testing | Functional testing and Bug fixing | 3
| Integration testing and Bug fixing | 2
Environment/Cloud Setup | Provisioning compute and storage | 5
integrate with guidewire instances
Network Setup | Network Generation | 5
Node configuration
Ecosystem Integration
Policy and Permissions | Asset,Policy and Permissions deployment on DLT network | 5
Packaging and Deployment | Application bundling | 5
Docker container management
Deployment script
| Total | 108