## Estimations
Sr No | Key | Summary | System | Complexity | UI Complexity | Middle Layer Complexity | Blockchain Complexity | Integration Complexity | Business Complexity | Efforts (In PD's) | Remarks
1 | BPSUL-44 | As a Country user, I need to log in into the application so that I can raise a request | IC | Simple | [5 empty] | 1 | Authentication
2 | BPSUL-45 | As a Intercompany user, I need to log into the application so that I can view and approve all requests | IC | Simple | [5 empty] | 1 | Authentication
3 | BPSUL-46 | Ability to Create users, based on country and access rights so that the right user roles can see the correct information | IC | Complex | Middle | Complex | Complex | Complex |  | 10 | User Management
4 | BPSUL-47 | Ability to grant access, based on country and access rights so that people have the correct access | IC | Medium | Complex | Simple | Simple | Medium |  | 5 | User Management
5 | BPSUL-48 | As an Admin user, I want to tracker the progress of my access request so that I can monitor the progress of my access | IC | [6 empty] | 5
6 | BPSUL-49 | As a user, I want a self-service option for passwords so that I can manage my password access | IC | Medium | Medium | Simple |  |  |  | 3 | Forgot Password
7 | BPSUL-50 | As a user, I want an error message so that I can see what information is incorrect when I try to log-in | IC | Simple | Simple | Simple |  |  |  | 2 | Authentication
8 | BPSUL-51 | As AR user, I want to input my AR request into Blockchain so that smart contracts can be executed and that I can process the request | IC | Medium | Medium | Medium | Simple | Complex |  | 20 | Include master data loading , validation, auto population, Request assignmnet etc
9 | BPSUL-52 | As CG user, I want to have the information on a repository so that RPA can process the information into AR SAP | IC | [6 empty] | 20 | Integration with Share Point - Batch job to pull/post data. Update ledger based on response
10 | BPSUL-53 | Ability of the robot to pull invoice number from SAP, so that I have the invoice number | IC | [7 empty] | Robo Task
11 | BPSUL-54 | As a requestor/user, I want to see the reference number on the dashboard so that I can monitor the request | IC | [6 empty] | 2 | Displaying reference number
12 | BPSUL-55 | As CG admin user, I want to check if the invoice was processed successfully so that I can check for any errors/issues | IC | [6 empty] | 5 | Batch job to read SAP response and update ledger
13 | BPSUL-56 | As a CG Admin, I want to be able to reject the request at AR processing stage so that only valid requests are approved | IC | [6 empty] | 5
14 | BPSUL-57 | Audit trail needed for any rejections at any stage, tied to requestor so that I can maintain a paper trail for audit purposes | IC | [6 empty] | 10 | Efforts not include detailed reporting. Based on detailed requirements on reports estimations would change.
15 | BPSUL-58 | As a AR user, I want to process invoices in Spanish so that I can send invoices for LATAM countries | IC | [6 empty] | 5 | Need more details on this. Internationalization not considered in scope
16 | BPSUL-59 | As a AR user, I want the MCO dashboard to be updated when a new invoice is created so that I can keep track of MCOs | IC | [6 empty] | 8 | New role for MCO to be added
17 | BPSUL-60 | As a AP user, I want to process MCO manually off the Blockchain so that I can process the invoice where exceptions occur | IC | [6 empty] | 2 | New role for MCO to be added. Need more details on this.
18 | BPSUL-61 | As a AR user, I want an RPA solution that picks up a PDF from a MCO email, attaches it and saves it in SAP and Sharepoint | IC | [7 empty] | Robo Task
19 | BPSUL-62 | As a AR/AP user, I want the Blockchain to handle exceptions per country and platform so that exceptions are handled correctly | IC | [6 empty] | 25 | Country-Platform exception handling. Estimations can be changed based on detailed requirements
20 | BPSUL-63 | As a CODA AR user, I want to link employees involved in training to one invoice so that training is charged correctly | IC | [7 empty] | Exception not disussed yet
21 | BPSUL-64 | As a Tax Approver, I want to be able to query any concerns so that I can apply the correct tax codes | IC | [7 empty] | AR or AP tax approver?
22 | BPSUL-65 | As a Tax Approver, I want to be able to reject request which have not applied the correct tax code so that only the correct tax code is applied | IC | [7 empty] | AR or AP tax approver?
23 | BPSUL-66 | As an AR user, I want an RPA solution for the posting in Trintech for GL, CC and tax codes re-class entry so that the correct tax is applied | IC | [7 empty] | Robo Task
24 | BPSUL-67 | As a AR user, I want the Blockchain to take a pause in the process until Trintech has been updated so that invoices are not processed before the correct tax is applied | IC | [7 empty] | Exception not disussed yet
25 | BPSUL-68 | As a AP user, I want business rules to check if both countries are in the EU so that I can apply the correct tax rates | IC | [7 empty] | Exception not disussed yet
26 | BPSUL-31 | As a CG FCCR user, I need super user access so that I can raise request on behalf of UL (not currently available) | FCCR
27 | BPSUL-32 | As a CG FCCR user, I want to have supporting documents available so that I have a audit trail available | FCCR
28 | BPSUL-33 | As a CG FCCR user, I want single requests and bulk requests to be processed the same so that they have the same outcome | FCCR
29 | BPSUL-34 | As a CG FCCR user, I want a threshold limit for exceptions so that I can meets SLAs | FCCR
30 | BPSUL-35 | As a CG FCCR user, I want to specify the source of the request so that I can trace the source and contact them if necessary | FCCR
31 | BPSUL-36 | As a CG FCCR user, I want to know the time taken to process a request so that I can track the speed to action requests | FCCR
32 | BPSUL-37 | As a CG FCCR user, I want to reconcile requests where possible so that to cost centres in SAP match what is available | FCCR
33 | BPSUL-38 | As a CG FCCR user, I want to see the history of the cost centre so that I can see/track any previous changes | FCCR
34 | BPSUL-39 | As a CG FCCR user, I want to help a UL requestor who can’t raise a request so that they can raise request without any question | FCCR
35 | BPSUL-40 | As a CG MDM user, I need the MDM data to be updated so that I can view the latest data | FCCR
36 | BPSUL-41 | As a CG MDM user, I want rules established to validate the data so that I can avoid duplication of data | FCCR
37 | BPSUL-42 | As a Capgemini MDM user, I want the Blockchain to update master data for MDM cost centre so that I can create and manage cost centres | FCCR
38 | BPSUL-43 | As a Capgemini MDM user, I want a robot that interacts with the MDG layer | FCCR
39 | BPSUL-21 | As a UL requestor, I want to log in to the FCCR system so that I can see the dashboard | FCCR
40 | BPSUL-69 | As a CG FCCR and MDM User, I want to have an operations dashboards so that I can manage day to day requests | FCCR
41 | BPSUL-70 | As a CG FCCR and MDM User, I want to have an managerial dashboard so that I can see if I am missing due dates | FCCR
42 | BPSUL-71 | As a CG FCCR and MDM User, I want to have an executive dashboard so that I can see if I am at risk | FCCR
43 | BPSUL-72 | As a CG FCCR and MDM User, I want to have a report of requests throughout the day so that I have an audit of transaction | FCCR
44 | BPSUL-22 | As a UL requestor, I want to have a real-time status update of the request so that I can track the progress of requests | FCCR
45 | BPSUL-23 | As a UL requestor, I want to differentiate between requests so that I can correctly tracks requests | FCCR
46 | BPSUL-24 | As a UL requestor, I want to create a cost centre for any region and any country with no segregation | FCCR
47 | BPSUL-25 | As a UL requestor, I want to be able to state when the cost centre will be active so that charges occur in the correct period | FCCR
48 | BPSUL-26 | As a UL requestor, I want the Blockchain upload to auto populate fields so that I can mass upload requests | FCCR
49 | BPSUL-27 | As a CG FCCR user, I want to auto-validate the rules at the request submission phase so that I can ensure the right information is included in actioning the request | FCCR
50 | BPSUL-28 | As a CG FCCR user, I want to improve the turnaround time so that I can meet SLAs. | FCCR
51 | BPSUL-29 | As a CG FCCR user, I want to avoid duplication when creating multiple cost centres so that only the correct number of cost centres are created | FCCR
52 | BPSUL-30 | As a CG FCCR user, I want a standardised template so that I can capture the correct information | FCCR
53 | BPSUL-73 | As a Blockchain Developer, I need to migrate the POC from HLF v1.0 to HLF v1.1 | IC | [6 empty] | 10
54 | BPSUL-76 | As a Blockchain Developer, I need to migrate Hyperledger Composer to Node SDK of Hyperledger Fabric | IC | [6 empty] | 10
55 | BPSUL-78 | As a Developer, I need to test the POC post migration testing | IC | [6 empty] | 1
|  | Email Notifications | IC | [6 empty] | 10 | Need more details on this.
|  | Angular Migration | IC | [6 empty] | 30
|  | Network Setup for Sundry. Create 6 organisations as per pilot and test POC in that environment. Network setup on developers machine. | IC | [6 empty] | 15
|  | Merging of Sundry Pilot code with with angular migrated code | IC | [6 empty] | 10
|  | Master data file format and template finalization | IC | [6 empty] | 5
|  | Functional and Integration Testing (Test Strategy Plan, Test Cases preparation and test case execution, Defect Fixing etc) | IC | [6 empty] | 20
|  | Design and Documentation(Service Spec,Data Modeling,Solution design etc) | IC | [6 empty] | 10
|  | Packaging and Deployment on Cloud environment. Testing on Cloud Environment and Defect Fixing | IC | [6 empty] | 15
|  | Contigency for Ad-hoc task | IC | [6 empty] | 25

## Resource Loading
Resource Name | Start Date | End Date | Role
Devendra Choudhary | 2018-07-23 | 408557 | Solution Architect
Sachin Patil | 2018-07-30 |  | Blockchain Designer
Purandam Mohanta | 2018-07-30 |  | Senior Blockchain Developer
Deepa Motwani | 408560 |  | Blockchain & Java Developer
Parth Rawal | 408560 |  | Blockchain & Java Developer
Tejal Tandale | 408582 |  | Blockchain & Java Developer
Amit Jain | 408574 |  | Senior Blockchain Developer
Ashu Gupta | 408574 |  | Blockchain & Java Developer
Vashwee Khokhar | 2018-07-30 |  | Scrum Master
Ronak Shah | 408571 |  | UI Developer
Sanjeev Gupta | 408560 |  | Delivery Manager and Architect
Puja Bhattad | 408571